## Slide 1: Development of a Homeless Strategic Plan for the City of Loveland
Burnes Center on Poverty and Homelessness
Graduate School of Social Work
@ The University of Denver

## Slide 2
Burnes Center on Poverty and Homelessness
The Burnes Center at the Graduate School of Social Work at the University of Denver was established in 2016 by Founder Don Burnes to serve as a think tank for the state, region, and nation on poverty and homelessness
Mission
The Burnes Center is to educate and partner with policymakers, practitioners and the public on issues of poverty, housing and homelessness to transform the lives of people who are homeless or at risk of becoming homeless.
Projects
- Adams County Project
-Beloved Community Village
- Bridging the Gap
- City of Trinidad
- CHASE
- Denver Social Impact Bond
- St. Francis

## Slide 3: Project Team
- Gary Sanford – Project Lead
Burnes Center on Poverty and Homelessness
- Zoe LeBeau, Katie Symons
LeBeau Development
- Jennifer Lopez
Project Moxie
- Vanessa Fenley
Consultant
- Margay Witzdam
Research Assistant

## Slide 4
OBJECTIVE:
Develop
a strategic
and actionable
plan to
address
homelessness
in Loveland
Colorado
PHASE 1:
Systems-level evaluation of current efforts
Collect and synthesize information
  Interview key stakeholders and survey providers and others not interviewed
  Gather information from those with lived experiences
Gain an understanding of local efforts
  Assess current system and services and identify areas of collaboration
  Analyze local policies and local data and identify gaps in housing and service continuum
Gather best practice information
  Identify efforts in similar sized communities
  Conduct research to identify best practices

## Slide 5
OBJECTIVE:
Develop
a strategic
and actionable
plan to
address
homelessness
in Loveland
Colorado
PHASE 2:
Develop an actionable management plan
Organize phase 1 information for review and discussion and determine broad goal areas
Review best practice information relative to gaps
Identify and prioritize objectives within goal areas
Determine short-, medium- and long- range tasks
Facilitate community meetings to gather input on preliminary goals and related tasks
Develop task time frames and identify persons responsible within actionable management plan

## Slide 6
PHASE 3:
Develop a Strategic Implementation Plan
- Finalize actionable management plan and provide recommendations in following areas:
  Governance body structure and role
  Current replication/expansion of successful efforts
  Use best practices – strengthen existing system
  Identify providers to address gaps
  Scaling resources and policies across Loveland
  Housing inventory with future needs
  Use of data to inform plan progress
  Incorporate those with lived experience
  Community education strategies
OBJECTIVE:
Develop
a strategic
and actionable
plan to
address
Homelessness
in Loveland
Colorado

## Slide 7
What is your approach to this plan?
- Incorporate a variety of voices and participation in plan development with collaborative involvement across sectors and geography.
- Ensure those with lived experience have meaningful roles in the process.
- Use data to drive understanding of current systems and outcomes.
- Transparency throughout the process.
- Create actionable strategies with measures.

## Slide 8: Anticipated Results Community ownership of the plan with local leadership and collaborations to guide implementation. Goals, measures and outcomes that guide efforts and can be adjusted along the way. Reduce duplication of services and increased efficiencies of available resources. Service providers view plan as a road map for future efforts. Persons experiencing homelessness are better served, and number of homeless households are decreased in the community.

## Slide 9: Development of a Homeless Strategic Plan for the City of Loveland Questions?
THANK YOU!​
​
Please contact Gary Sanford gary.sanford@du.edu or Margay Witzdam
stevie.witzdam@du.edu with any questions, comments or concerns regarding the project.​
​